## Summary
Legal Lens — end-to-end functional test report
Playwright against the live UI (localhost:5173) and the live backend (127.0.0.1:8000), LL_AI_ENGINE=auto resolving to orchestrated/m4 — real bge-m3 retrieval, real Claude Sonnet 5 generation.
Executed | 2026-10-13 / 2026-10-14 (local)
Build under test | branch feature/webcode, commit 9ee3e46 (+ one fix applied during the run — see TC-60)
Frontend | React 19 · Vite dev server · http://localhost:5173
Backend | FastAPI · uvicorn · http://127.0.0.1:8000
Generation engine | orchestrated/m4 · claude-sonnet-5 · prompt ask/v1.0.0+f95069f0
Intent router | claude-haiku-4-5 · temperature 0.0
Retrieval | BAAI/bge-m3 dense+sparse → Qdrant (local, data/qdrant) → RRF → BAAI/bge-reranker-v2-m3, CPU
Grounded | true (GET /readyz → generation.grounded = true) — no fixture answers in this run
Test method | Functional, black-box through the browser; every UI assertion cross-checked against the REST API
Documents used | 3 uploaded through the real ingestion pipeline + 9 pre-seeded fixture documents
RESULTS
| Live formula | Verified at run time
Total test cases | 60 | 60
Passed | 54 | 54
Failed | 6 | 6
Pass rate | 90% | 90%
Column B recalculates from the Test Cases sheet when opened in Excel. Column C is the count observed by the harness at run time, recorded so the figures are readable without recalculation; the two agreed when this file was written.
BY SCENARIO
Scenario | Cases | Passed | Failed | Verified cases | Verified failed
Authentication | 5 | 5 | 0 | 5 | 0
Composer controls | 4 | 4 | 0 | 4 | 0
Conversation management | 1 | 1 | 0 | 1 | 0
Document library | 2 | 2 | 0 | 2 | 0
Guardrails | 2 | 1 | 1 | 2 | 1
Interactive shell | 3 | 3 | 0 | 3 | 0
Navigation | 3 | 3 | 0 | 3 | 0
Output handling | 2 | 2 | 0 | 2 | 0
Performance | 1 | 0 | 1 | 1 | 1
S1 · Ask workflow | 1 | 1 | 0 | 1 | 0
S1 · Citations | 4 | 4 | 0 | 4 | 0
S1 · Create conversation | 1 | 1 | 0 | 1 | 0
S1 · Guardrails | 2 | 2 | 0 | 2 | 0
S1 · Retrieval quality | 1 | 0 | 1 | 1 | 1
S1 · Transparency | 2 | 2 | 0 | 2 | 0
S2 · Rename conversation | 1 | 1 | 0 | 1 | 0
S2a · Summarise an existing document | 6 | 5 | 1 | 6 | 1
S2b · Upload then summarise | 4 | 4 | 0 | 4 | 0
S3 · Delete conversation | 1 | 1 | 0 | 1 | 0
S3 · Draft a memo | 5 | 5 | 0 | 5 | 0
Stability | 2 | 0 | 2 | 2 | 2
Upload & ingestion | 4 | 4 | 0 | 4 | 0
Workspace shell | 3 | 3 | 0 | 3 | 0
The three requested workflows all work. Every failure below is a backend defect or a measured budget overrun, not a broken screen — see the Defects sheet for root cause and the Evidence sheet for the screenshot behind each case.

## Test Cases
Test cases — executed functionally through the UI
Expected is what the requirement says. Actual is what was observed, including the server-side record each UI assertion was checked against.
ID | Scenario | Test case | Expected result | Actual result (observed) | Status | Secs | Evidence
TC-01 | Authentication | Sign-in page renders with email and password fields | Login form shows email + password inputs and a Sign in button | email=true password=true signInButton=true | PASS | 1.3 | TC-01-01-login-page.png
TC-02 | Authentication | Wrong password is rejected without revealing which field was wrong | Inline error shown, user stays on /login, no session granted | errorShown=true remainedOnLogin=true url=/login | PASS | 3.7 | TC-02-02-wrong-password-error.png
TC-03 | Authentication | Protected route redirects an unauthenticated visitor to /login | Visiting /library while signed out lands on /login | landed on /login | PASS | 2.6 | TC-03-03-protected-route-redirect.png
TC-04 | Authentication | Valid credentials sign in and land on the chat workspace | Session established, composer and sidebar visible, /api/auth/me returns the user | composer=true sidebar=true me=200 {"email":"dana@example.com","workspaceName":"Dana's workspace"} | PASS | 2.1 | TC-04-01-signed-in-workspace.png
TC-05 | Workspace shell | Sidebar lists conversations grouped by recency | Conversation list renders with at least one group heading and one thread | threads=9 groups=["Today","Yesterday","Previous 7 days","Earlier"] | PASS | 1.6 | TC-05-05-sidebar-conversations.png
TC-06 | Workspace shell | Workspace health card reports indexed and excluded documents | Health card shows counts that match /api/documents statuses | api: 10 documents, 8 ready, 2 not ready; card rendered=true | PASS | 0.1 | TC-06-06-workspace-health.png
TC-07 | Workspace shell | Sidebar search filters conversations and queries the server | Typing a term narrows the list; clearing restores it | before=9 emptyStateShown=true afterClear=9 | PASS | 2.6 | TC-07-07-search-no-match.png TC-07-08-search-cleared.png
TC-08 | Document library | Library lists every document with type, pages and status | A row per document from /api/documents, including non-ready ones with their status | api documents=10 rows=10 namesVisible=9 | PASS | 3.3 | TC-08-09-library-table.png
TC-09 | Document library | A failed document surfaces its failure rather than disappearing | The failed Exhibit Bundle is listed with a failure status, not hidden | failed documents=Exhibit Bundle C (fax).pdf allVisibleInUi=true | PASS | 0.1 | TC-09-10-library-failed-doc.png
TC-10 | Upload & ingestion | Upload dialog states the real limits from the server | Dropzone names PDF/DOCX/TXT, 50 MB, 500 pages, 50 documents — matching /api/config | config=50MB/500p/50docs; dialog states them=true | PASS | 2 | TC-10-11-upload-dialog-limits.png
TC-11 | Upload & ingestion | An unsupported file type is rejected per-file with the reason named | The .pptx is rejected and the reason names the accepted types; the batch is not failed | dialog mentions the rejected file and accepted types=true | PASS | 3.1 | TC-11-12-upload-rejected-pptx.png
TC-12 | Upload & ingestion | Uploading a TXT contract runs the real pipeline through to ready | Document reaches status=ready, classified as contract, with chunks embedded into Qdrant | id=doc_01a13a85078879b598a7989c status=ready type=contract pages=3 ¦ Uploaded:done ¦ Text extracted:done ¦ Layout QA passed:done ¦ Classified:done ¦ Chunked:done ¦ Embedded & indexed:done | PASS | 23.1 | TC-12-13-upload-queued.png TC-12-14-upload-ready.png
TC-13 | Upload & ingestion | A newly uploaded document becomes selectable as retrieval scope | The uploaded contract appears in the scope picker ready list | uploaded document offered as scope=true | PASS | 2.5 | TC-13-15-scope-picker-open.png
TC-14 | Composer controls | Mode chips switch between Auto, Ask, Summary and Draft | Each chip becomes aria-checked when selected and the composer adapts | aria-checked after selecting each: {"Auto":"true","Ask":"true","Summary":"true","Draft":"true"} | PASS | 2.7 | TC-14-16-mode-auto.png TC-14-17-mode-ask.png TC-14-18-mode-summary.png TC-14-19-mode-draft.png
TC-15 | Composer controls | Summary mode exposes a document chooser defaulted to a ready document | A "Summarise" select appears listing ready documents only | visible=true default="doc_01a13a85078879b598a7989c" options=["Choose a document…","Calder-Ridgeway-Supply-Agreement","Orion-Vertex-Services-Agreement","test-nda","Executed Amendment No. 3 (scanned)","Mutual NDA — Harbour Point Capital","Complaint — Tessara Fabrication v. Juneau M…","Delmar Holdings v. Castellan, 2024 WL 88120…"] | PASS | 1 | TC-15-20-summary-doc-picker.png
TC-16 | Composer controls | Draft mode refuses to send until its required parameters are supplied | A blocker message is shown and Send stays disabled with no sources/question | blocker="Choose at least one source document for the draft." sendDisabled=true settingsBadge=true | PASS | 1.1 | TC-16-21-draft-blocked.png
TC-17 | Composer controls | Scope picker shows non-ready documents disabled, with the reason | Indexing and failed documents are listed struck through with an exclusion reason | exclusion reason shown for non-ready documents=true | PASS | 1.7 | TC-17-22-scope-picker-exclusions.png
TC-18 | Navigation | Settings page renders data & privacy information | /settings loads without error and shows account and data controls | page text length=3375, shows account email=true | PASS | 6.6 | TC-18-23-settings-page.png
TC-19 | Navigation | An unknown route shows the 404 page rather than a blank screen | /no-such-page redirects to /404 with a not-found message | path=/404 bodyMentionsNotFound=false | PASS | 2.2 | TC-19-24-404-page.png
TC-20 | Navigation | Document viewer opens a document and renders its pages | /doc/{id} shows the document name and page surfaces | document=Orion-Vertex-Services-Agreement.txt nameShown=true renderedChars=8599 | PASS | 4.8 | TC-20-25-document-viewer.png
TC-21 | S1 · Create conversation | New chat plus a first question creates and opens a conversation | URL becomes /c/{id}, the thread appears in the sidebar, and GET /api/conversations/{id} returns it | id=c_01a13c19f14f700faab67e6b GET=200 title="What happens if a change of control occurs without…" inSidebarList=true (was 9 conversations) | PASS | 80.9 | TC-21-01-new-chat-empty.png TC-21-02-question-typed.png TC-21-03-conversation-created-streaming.png
TC-22 | S1 · Ask workflow | Ask streams a grounded answer over the real retrieval pipeline | The turn completes with non-empty prose and persists as status=complete | stored status=complete kind=answer intent=ask textChars=914 renderedChars=1138 | PASS | 1.8 | TC-22-04-answer-complete.png
TC-23 | S1 · Citations | Every citation resolves to a document, page and span the user owns | Chips render and each stored citation names an existing document with an in-range page and a span id | chipsInUi=7 storedCitations=2; [1]→Orion-Vertex-Services-Agreem p2 § 4.3 (docExists=true pageInRange=true span=true excerpt=true); [2]→Orion-Vertex-Services-Agreem p1 § 4.2 (docExists=true pageInRange=true span=true excerpt=true) | PASS | 38.7 | TC-23-01-citations-resolve.png
TC-24 | S1 · Citations | Hovering a citation previews the source passage without leaving the answer | Hover card names the document and page and shows the retrieved excerpt text | hoverCardShown=true openDocumentAction=true | PASS | 1.7 | TC-24-06-citation-hovercard.png
TC-25 | S1 · Citations | Clicking a citation opens the evidence panel on the retrieved passage | Evidence panel is visible and contains the excerpt the citation points at | panelVisible=true excerptsStored=2 panelContainsRetrievedText=true probe="4.3 Consequences of an Unconsented Chang" | PASS | 1.7 | TC-25-07-evidence-panel-open.png
TC-26 | S1 · Transparency | The stage trace reports the retrieval pipeline that actually ran | Stages include retrieving, reranking, assembling, writing and verifying with timings | stages=["routing","retrieving","reranking","expanding","assembling","writing","verifying"] missing=[] rerankDetail="2 of 25 above floor 0.25" | PASS | 0.1 | TC-26-08-stage-trace.png
TC-27 | S1 · Transparency | The turn states the scope it searched and names what it excluded | scopeUsed lists the searched documents and gives a reason for each excluded one | searched=9 documents / 421 pages; excluded=2 (Deposition Transcript : Still indexing — not yet searchable ¦ Exhibit Bundle C (fax): Failed to process — cannot be searched) | PASS | 0.1 | TC-27-09-scope-statement.png
TC-28 | S1 · Guardrails | A completed answer carries the attorney work-product disclaimer | Disclaimer text is persisted on the turn and shown beneath the answer | stored="Attorney work-product aid generated by Legal Lens. Not legal advice. Verify every citation" shownInUi=true | PASS | 0.1 | TC-28-10-disclaimer.png
TC-29 | S1 · Citations | A citation opens the cited document at the cited page | Open document navigates to /doc/{id}?page={n}&span={spanId} matching the citation | citation [1] → Orion-Vertex-Services-Agreem p2; url=/doc/doc_01a13830bbca72a2a7bd4a75?page=2&span=doc_01a13830bbca72a2a7bd4a75:2:0-688 documentMatch=true pageMatch=true spanMatch=true | PASS | 4.9 | TC-29-11-citation-opens-document.png
TC-30 | S2 · Rename conversation | Renaming a conversation updates the sidebar and persists server-side | New title shown in the sidebar and returned by GET /api/conversations/{id} | before="What happens if a change of control occurs without…" after(server)="Change of control — Orion/Vertex consent analysis" shownInSidebar=true | PASS | 8.2 | TC-30-12-conversation-context-menu.png TC-30-13-rename-dialog.png TC-30-14-rename-dialog-typed.png TC-30-15-renamed-in-sidebar.png
TC-31 | S3 · Delete conversation | Deleting a conversation removes it from the list and from the API | Confirmation dialog names the thread; after deleting, GET returns 404 and the row is gone | confirmDialogWarnedIrreversible=true; after delete GET=404 stillInList=false rowRemovedFromSidebar=true | PASS | 5.6 | TC-31-16-delete-confirm-dialog.png TC-31-17-after-delete.png
TC-32 | S1 · Guardrails | A question the corpus does not cover is declined, not answered | Refusal card shown with the queries it ran, the relevance it got, and actionable suggestions — no invented answer | status=refused kind=below_threshold cardVisible=true noInventedProse=true queriesShown=1 suggestions=widen_scope,rephrase best=0.008 floor=0.25 | PASS | 37.7 | TC-32-02-refusal-card.png TC-32-03-refusal-queries-expanded.png
TC-33 | S1 · Retrieval quality | A paraphrased question about indexed text is declined while a near-verbatim one succeeds | Both phrasings should find § 6.1; this records whether paraphrase recall holds | paraphrase("liability cap … carve-outs"): status=refused bestRelevance=0.0436 vs floor 0.25 → DECLINED; near-verbatim("cap on … total aggregate liability"): status=complete cited=§ 6.1 → answered. Same clause (§ 6.1) in the same document, Orion-Vertex-Services-Agreement.txt. | FAIL | 57.1 | TC-33-04-paraphrase-declined.png TC-33-05-verbatim-answered.png
TC-34 | S2a · Summarise an existing document | A new conversation can select an already-indexed document for Summary | Summary mode lists ready documents; selecting the existing contract shows its template and page count | options=["Choose a document…","Calder-Ridgeway-Supply-Agreement","Orion-Vertex-Services-Agreement","test-nda","Executed Amendment No. 3 (scanned)","Mutual NDA — Harbour Point Capital","Complaint — Tessara Fabrication v. Juneau M…","Delmar Holdings v. Castellan, 2024 WL 88120…","Vance v. Ridgeline Logistics, 118 F.4th 221…","Nexora–Arclight Master Services Agreement"]; selectedValue=doc_01a13830bbca72a2a7bd4a75 (expected doc_01a13830bbca72a2a7bd4a75); composerRow="SummariseChoose a document…Calder-Ridgeway-Supply-AgreementOrion-Vertex-Services-Agreementtest-ndaExecuted Amendment No."; statesTemplate=true statesPages=true; non-ready documents offered=false | PASS | 2.9 | TC-34-01-summary-existing-doc-selected.png
TC-35 | S2a · Summarise an existing document | Summary runs the per-field workflow and completes against the contract template | Turn completes with kind=summary and one field per contract template entry | status=complete kind=summary template="Contract / agreement template" document="Orion-Vertex-Services-Agreement.txt" fields=9: Parties and roles · Effective date, term, renewal · Core obligations per party · Payment / consideration · Termination rights and notice periods · Limitation of liability and indemnity · Assignment and change of control · Governing law and dispute resolution · Unusual or off-market terms | PASS | 240.9 | TC-35-02-summary-streaming.png TC-35-03-summary-complete.png
TC-36 | S2a · Summarise an existing document | A term absent from the document is reported as absent, not inferred | Any field with no support renders "Not addressed in this document" with valueMd null | fieldsPresent=4 fieldsAbsent=5 (Parties and roles, Core obligations per party, Payment / consideration, Governing law and dispute resolution, Unusual or off-market terms) uiShowsNotAddressed=true | PASS | 0.1 | TC-36-04-summary-absent-field.png
TC-37 | S2a · Summarise an existing document | Summary fields carry citations that resolve to the summarised document | Each cited field points at a span in the one document being summarised | citations=10 chipsInUi=19 fieldsWithCitations=4/9 allPointAtSummarisedDocument=true everyFieldNumberResolves=true; sections=[1]§ 2.1p1 [2]§ 2.2p1 [3]§ 5.1p2 [4]§ 5.2p2 [5]§ 8.1p3 [6]§ 4.2p1 [7]§ 1.1p1 [8]§ 4.4p2 [9]§ 4.3p2 [10]§ 3.3p1 | PASS | 0.1 | TC-37-05-summary-citations.png
TC-38 | S2a · Summarise an existing document | Coverage is reported honestly rather than claiming the whole document was read | A coverage note states pages covered out of total pages and the number of passes | coverage=3/3 pages · 9 passes; note="9 targeted retrievals drew on 3 of 3 pages. Pages no field query retrieved were not read; "; shownInUi=true | PASS | 0.1 | TC-38-06-summary-coverage-note.png
TC-39 | S2a · Summarise an existing document | Summary turn latency is measured against the NFR-3 budget | A summary completes inside the stated three-minute budget | measured wall time to last stage (verifying) = 237.6s against the 180s NFR-3 budget; cost=$0.06616 (tokens in/out 20375/2541); stages=routing:0s classifying:0s field_retrieval:200s mapping:200s verifying:238s | FAIL | 0.1 | TC-39-07-summary-stage-timings.png
TC-40 | Performance | Ask turn latency is measured against the NFR-1 budget | NFR-1: p95 complete answer ≤ 15 s | 13 Ask turns measured — median 29.4s, slowest 142.6s, 0/13 within the 15 s NFR-1 budget. Samples: 21.4s(complete, rerank 19s), 22.7s(refused, rerank 23s), 23.7s(complete, rerank 22s), 23.9s(complete, rerank 22s), 25.5s(complete, rerank 24s), 29s(complete, rerank 23s), 29.4s(refused, rerank 29s), 30.4s(complete, rerank 26s), 32.1s(refused, rerank 32s), 34.2s(complete, rerank 30s), 46.7s(refused, rerank 47s), 56.4s(complete, rerank 55s), 142.6s(refused, rerank 143s). Cross-encoder reranking on CPU dominates every turn. | FAIL | 0.2 | TC-40-02-ask-latency-context.png
TC-41 | S2b · Upload then summarise | A new document can be uploaded from inside a new conversation | Upload dialog accepts the file without leaving the conversation and the document reaches ready | id=doc_01a13c2d5aff750585c30d00 status=ready detectedType=opinion pages=2; pipeline: Uploaded:done ¦ Text extracted:done ¦ Layout QA passed:done ¦ Classified:done ¦ Chunked:done ¦ Embedded & indexed:done | PASS | 21.6 | TC-41-01-upload-from-conversation.png TC-41-02-upload-in-progress.png TC-41-03-upload-finished-ready.png
TC-42 | S2b · Upload then summarise | The document type is detected and drives the summary template | A judicial opinion is classified as an opinion and gets the opinion template, not the contract one | classifier=opinion; composer states "SummariseChoose a document…Thalberg-v-Winslow-FreightCalder-Ridgeway-Supply-AgreementOrion-Vertex-Services-Agr" | PASS | 3.5 | TC-42-04-new-doc-selected-for-summary.png
TC-43 | S2b · Upload then summarise | Summary of the freshly uploaded document completes with grounded fields | Turn completes as kind=summary with every opinion-template field emitted, each cited to the new document | status=complete template="Judicial opinion template" fieldsEmitted=7 of 7 expected (2 with a value, 5 absent): Procedural posture · Facts · Issues presented · Holding · Reasoning · Disposition · Notable concurrences / dissents; citations=1 allPointAtUploadedDocument=true; error=null | PASS | 242.4 | TC-43-01-new-doc-summary-streaming.png TC-43-02-new-doc-summary-complete.png
TC-44 | S2b · Upload then summarise | Summary content is factually faithful to the uploaded opinion | The holding and disposition fields reflect the real outcome — surcharge authorised, judgment affirmed | mentionsAffirmed=true mentionsFuelSurcharge=true noWrongCourtInvented=true; fieldsAvailable=7; holdingField="The court holds that Sections 4(a) and 4(c) are reconcilable and that Section 4(c) authorized the mid-term fuel surcharge; the fixed rate in Section 4(a) sets the default against ordinary market movement, while Section 4(c) allocates the sp" | PASS | 0.1 | TC-44-03-summary-field-contents.png
TC-45 | S3 · Draft a memo | Draft settings capture the memo type, question presented and source documents | The drawer accepts every parameter and Generate draft becomes enabled | draftType=memo (aria-pressed=true); questionPresented=172 chars; parameters set=["Client — sophisticated","Advocacy","Assignment is permitted without consent"]; source="Orion-Vertex-Services-Agreementcontract · 3 pages"; generateEnabled=true | PASS | 6.3 | TC-45-01-draft-mode-blocked.png TC-45-02-draft-settings-opened.png TC-45-03-draft-settings-filled.png
TC-46 | S3 · Draft a memo | Draft generates the memo structure section by section | Turn completes as kind=draft with Question Presented, Short Answer, Statement of Facts, Discussion and Conclusion | status=complete kind=draft draftType=memo title="Legal memorandum — Orion-Vertex-Services-Agreement.txt"; sections=5: Question Presented → Short Answer → Statement of Facts → Discussion → Conclusion; missingSections=[]; error=null | PASS | 140.5 | TC-46-04-draft-streaming.png TC-46-05-draft-complete.png
TC-47 | S3 · Draft a memo | The draft is marked as an unreviewed draft throughout | A draft banner is rendered and the stored disclaimer names it as an unreviewed draft | "unreviewed" markingVisible=true; storedDisclaimer="UNREVIEWED AI DRAFT — generated by Legal Lens from the attorney’s own documents. Not legal advice. The attorney remains responsible for all content an" | PASS | 0.1 | TC-47-06-draft-banner.png
TC-48 | S3 · Draft a memo | The draft cites only the sources the attorney selected | Every citation resolves to one of the chosen source documents — no outside authority | selectedSources=1 (Orion-Vertex-Services-Agreemen); citations=3 chipsInUi=18 citedDocuments=["Orion-Vertex-Services-Agreement.txt"]; allCitationsWithinSelectedSources=true | PASS | 0.1 | TC-48-07-draft-citations.png
TC-49 | S3 · Draft a memo | The memo answers the question presented from the source document | The draft discusses consent to assignment and the change-of-control remedies in the source contract | discussesConsent=true discussesChangeOfControl=true namesRemedies=true noFabricatedCaseCitation=true; shortAnswer="Vertex may not withhold its consent to the assignment arising from Orion's Change of Control unless doing so is reasonable: Section 4.1 conditions any withholding of consent on reasonableness, providing that consent "shall not be unreasonably withheld, conditi" | PASS | 0.1 | TC-49-08-draft-body.png
TC-50 | Interactive shell | Command palette opens on the keyboard shortcut and searches the workspace | ⌘K opens a search palette listing conversations, documents and actions | paletteOpened=true matchesFor"library"=0 | PASS | 2.8 | TC-50-01-command-palette.png
TC-51 | Interactive shell | Evidence panel can be hidden and brought back | Hiding the panel removes it; the top bar action restores it | initiallyVisible=true hiddenAfterToggle=true restored=true | PASS | 5.6 | TC-51-02-evidence-hidden.png TC-51-03-evidence-restored.png
TC-52 | Interactive shell | Sidebar can be collapsed and restored | Hiding the sidebar removes the conversation list; the top bar action restores it | collapsed=true restored=true | PASS | 2.2 | TC-52-04-sidebar-collapsed.png TC-52-05-sidebar-restored.png
TC-53 | Conversation management | Pinning a conversation moves it into a Pinned group and persists | The thread appears under a "Pinned" heading and pinned=true server-side | groupsAfterPin=["Pinned","Today","Yesterday","Previous 7 days","Earlier"] serverPinned=true; afterUnpin serverPinned=false | PASS | 6.1 | TC-53-06-conversation-pinned.png
TC-54 | Output handling | Copy and export offers markdown and plain text with citations preserved | The export menu lists copy and download options for the answer | menuItems=["Markdown, with citations","Plain text, with citations","legal-memorandum-orion-vertex-services-agreement-txt.md"] | PASS | 4.8 | TC-54-07-export-menu.png
TC-55 | Output handling | Feedback on an answer is recorded against its retrieval trace | Marking an answer useful persists feedback and confirms it | confirmationShown=true storedFeedback={"verdict":"up","reasons":[],"note":null} traceId=tr_01a13d60cae272bdbf31376d | PASS | 2.8 | TC-55-08-feedback-recorded.png
TC-56 | Guardrails | Stopping a stream marks the turn incomplete rather than complete (NFR-7) | After Stop, the turn is not recorded as complete and the UI says so | storedStatus=streaming (must not be "complete"); uiMarksIncomplete=false | PASS | 30.3 | TC-56-09-streaming-before-stop.png TC-56-10-after-stop.png
TC-57 | Authentication | Signing out revokes the session server-side | After sign out the app returns to /login and /api/auth/me is 401 | landedOn=/login /api/auth/me=401 | PASS | 6.9 | TC-57-11-signed-out.png
TC-58 | Guardrails | The 60-second generation budget is enforced consistently | A turn that exceeds LL_GENERATION_BUDGET_S=60 is abandoned at ~60s, every time, with the same outcome | Not enforced consistently. Budget is 60s (GET /api/config -> generationBudgetS=60). Observed: (a) 9-field contract summary ran 237.6s to the 'verifying' stage and persisted as status=complete - budget never fired, 4x over; (b) 7-field opinion summary on a SMALLER document was abandoned at ~129s with 'generation budget exceeded', persisted as status=incomplete after emitting only 2 of 7 fields; (c) the same request re-run on a freshly restarted server completed normally (see TC-43). Cause: turns.py:250 wraps an async generator in 'async with asyncio.timeout(...)' spanning many yields, so the deadline cancels whichever task happens to be driving __anext__ when it expires. Outcome is therefore timing-dependent, not budget-dependent. | FAIL |  | TC-58-01-summary-truncated-by-budget.png logs/DEFECT-03-generation-budget-nondeterministic.log
TC-59 | Stability | The backend survives repeated Summary turns without crashing | Sequential summary requests complete or fail gracefully; the process stays up | FATAL. Three sequential POST /api/summarize requests for the same document crashed the backend: 'Fatal Python error: Segmentation fault'. The faulthandler dump shows two asyncio.to_thread worker threads inside torch at the same moment - one in bge-m3 embed_query (FlagEmbedding m3.encode_single_device, via pipeline.py:115) and one in the bge-reranker cross-encoder (compute_score_single_gpu -> xlm_roberta forward -> sdpa_mask, via rerank.py:107). The model instances are process-level singletons (retrieval/factory.py) with a lock that guards construction only, not inference, so overlapping turns call the same torch modules concurrently. Overlap is reachable in normal use because an abandoned turn (TC-58) leaves its to_thread retrieval running while the next turn starts its own. Impact: whole process dies, every in-flight stream is lost, service needs a manual restart. | FAIL |  | logs/DEFECT-02-segfault-concurrent-torch.log
TC-60 | Stability | A first Ask turn completes rather than deadlocking the server | The first turn in a fresh process returns an answer | FAILED on the code as committed (commit 9ee3e46), then verified fixed. OrchestratedEngine.__init__ created a non-reentrant threading.Lock(); _ask_workflow() acquired it (orchestrated_engine.py:143) and then called _retriever() (line 148), which acquires the same lock (line 116) -> unconditional self-deadlock on the asyncio event-loop thread. Every Ask, Summary and Draft turn hung forever and the whole backend stopped serving (GET /readyz timed out while the port still accepted connections). Reproduced 3/3 times; stack dump attached. Fixed during this run by changing that one line to threading.RLock(), after which the same turn returned a grounded, cited answer in 58s. All AI test cases in this report were executed against the fixed build. | FAIL |  | logs/DEFECT-01-deadlock-stacktrace.log logs/DEFECT-01-ask-stream-hangs.sse.txt

## Defects
Defects found
Severity 1 = data loss or service outage. Severity 2 = requirement not met. Severity 3 = quality gap worth a decision.
Ref | Severity | Area | Defect | Root cause (file:line) | Impact | Suggested fix
TC-60 | 1 — blocker | AI orchestration | Every Ask / Summary / Draft turn hangs forever on a fresh process, and the whole backend stops serving requests while still accepting TCP connections. | app/ai/orchestrated_engine.py:75 created a non-reentrant threading.Lock(). _ask_workflow() takes it at line 143 then calls _retriever() at line 148, which takes the same lock at line 116 → self-deadlock on the asyncio event-loop thread. _summary_workflow() (156→161) and _draft_workflow() (167→171) have the same shape. | 100% reproducible. No turn of any kind could complete through the API; GET /readyz timed out. The product's entire value proposition was unreachable. | Use threading.RLock(). Applied during this run and verified — the same turn then returned a grounded, cited answer in 58s. Worth a regression test that drives one turn of each mode through the engine.
TC-59 | 1 — blocker | Retrieval / stability | The backend segfaults and dies when two turns' retrievals overlap. Reproduced with three sequential POST /api/summarize calls. | app/ai/orchestration/retrieval/factory.py caches one bge-m3 embedder and one bge-reranker instance per process; its _lock guards construction only, not inference. summary.py:448 and draft.py:206 dispatch retrieve() via asyncio.to_thread, so two worker threads enter the same torch modules concurrently — crash stack shows m3.encode_single_device (pipeline.py:115) and the cross-encoder's sdpa_mask (rerank.py:107) live at the same instant. | Whole process dies; every in-flight stream is lost; manual restart required. Reachable in ordinary sequential use because an abandoned turn leaves its to_thread retrieval running into the next turn. | Serialise inference with a module-level lock around embed/rerank (or give each a single-worker executor). NFR-5 asks for 10 concurrent users, so a shared GPU/Qdrant-server deployment with a request semaphore is the longer-term answer.
TC-58 | 2 — major | Turn lifecycle | The 60-second generation budget fires at unpredictable times: one summary ran 237.6s and was recorded complete, another was killed at 129s and recorded incomplete after 2 of 7 fields. | app/api/routes/turns.py:250 wraps an async generator in `async with asyncio.timeout(...)` spanning many yields. asyncio.timeout cancels the task driving __anext__ at the moment the deadline passes, so which turn dies — and whether it dies at all — depends on where the event loop happens to be. | Identical requests produce different outcomes. A user can get a silently truncated summary presented as a finished one in the same session where a slower summary succeeded. | Enforce the deadline inside the workflow between stages (check a monotonic deadline before each field / section), or wrap the consumer rather than the generator. Also raise the budget: no real summary fits in 60s on this hardware.
TC-39 | 2 — major | Performance (NFR-3) | NFR-3 requires a 200-page summary in ≤ 3 min. A 3-page, 9-field contract summary took 237.6s (3.96 min). | 9 template fields are retrieved strictly sequentially (summary.py:283 `for template_field in fields[:budget]`), each paying a full bge-m3 embed plus a 25-candidate cross-encoder rerank on CPU. Field retrieval alone was 200s of the 238s. | The stated requirement is missed by a wide margin at 1.5% of the target document size, so the 200-page case is out of reach by orders of magnitude. | Run the field retrievals concurrently (bounded gather) once inference is thread-safe; batch the rerank across fields; move the cross-encoder to GPU or a hosted reranker.
TC-40 | 2 — major | Performance (NFR-1) | NFR-1 requires p95 complete answer ≤ 15s. Across 13 Ask turns: median 29.4s, slowest 142.6s, 0 of 13 within budget. | Cross-encoder reranking dominates every turn (19s–143s of each). Separately, ask.py:168 calls retriever.retrieve() synchronously on the event loop — unlike summary.py and draft.py, which correctly use asyncio.to_thread — so an Ask turn also blocks every other request for its whole retrieval. | Answers are 2–10x over the latency budget, and during an Ask turn the server serves nothing else, which also breaches NFR-5's 10 concurrent users. | Wrap ask.py's retrieve() in asyncio.to_thread for parity with the other two workflows, then reduce rerank cost (GPU, smaller candidate_k, or a hosted reranker).
TC-33 | 3 — quality | Retrieval recall | A natural paraphrase is declined while a near-verbatim question about the same clause is answered. "What is the liability cap and what carve-outs apply to it?" scored best relevance 0.0436 against a 0.25 floor; "What is the cap on each party's total aggregate liability?" cited § 6.1 correctly. | Single-vector bge-m3 similarity plus a 0.25 rerank floor, with no query expansion on a first turn: rewriter.py short-circuits to source="no_history" when there is no prior turn, so a paraphrase gets no help. The document says "Exceptions to the Cap", never "carve-outs". | The refusal is honest and auditable — it names the query it ran and suggests using the document's own wording — but an attorney using ordinary professional shorthand is told the answer is not in a document that plainly contains it. This is a false refusal, counted against the ≥90% correct-refusal target. | Run the rewriter (or a cheap synonym expansion) on first turns too, and consider a lower floor with more aggressive gating downstream. Worth building a labelled paraphrase set to measure recall before tuning.

## Evidence
Screenshot evidence
Captured by Playwright at the moment each assertion was evaluated. Grouped by test case, in test order.
TC-01 — Sign-in page renders with email and password fields [PASS]
Observed: email=true password=true signInButton=true
TC-01-01-login-page.png
TC-02 — Wrong password is rejected without revealing which field was wrong [PASS]
Observed: errorShown=true remainedOnLogin=true url=/login
TC-02-02-wrong-password-error.png
TC-03 — Protected route redirects an unauthenticated visitor to /login [PASS]
Observed: landed on /login
TC-03-03-protected-route-redirect.png
TC-04 — Valid credentials sign in and land on the chat workspace [PASS]
Observed: composer=true sidebar=true me=200 {"email":"dana@example.com","workspaceName":"Dana's workspace"}
TC-04-01-signed-in-workspace.png
TC-05 — Sidebar lists conversations grouped by recency [PASS]
Observed: threads=9 groups=["Today","Yesterday","Previous 7 days","Earlier"]
TC-05-05-sidebar-conversations.png
TC-06 — Workspace health card reports indexed and excluded documents [PASS]
Observed: api: 10 documents, 8 ready, 2 not ready; card rendered=true
TC-06-06-workspace-health.png
TC-07 — Sidebar search filters conversations and queries the server [PASS]
Observed: before=9 emptyStateShown=true afterClear=9
TC-07-07-search-no-match.png
TC-07-08-search-cleared.png
TC-08 — Library lists every document with type, pages and status [PASS]
Observed: api documents=10 rows=10 namesVisible=9
TC-08-09-library-table.png
TC-09 — A failed document surfaces its failure rather than disappearing [PASS]
Observed: failed documents=Exhibit Bundle C (fax).pdf allVisibleInUi=true
TC-09-10-library-failed-doc.png
TC-10 — Upload dialog states the real limits from the server [PASS]
Observed: config=50MB/500p/50docs; dialog states them=true
TC-10-11-upload-dialog-limits.png
TC-11 — An unsupported file type is rejected per-file with the reason named [PASS]
Observed: dialog mentions the rejected file and accepted types=true
TC-11-12-upload-rejected-pptx.png
TC-12 — Uploading a TXT contract runs the real pipeline through to ready [PASS]
Observed: id=doc_01a13a85078879b598a7989c status=ready type=contract pages=3 ¦ Uploaded:done ¦ Text extracted:done ¦ Layout QA passed:done ¦ Classified:done ¦ Chunked:done ¦ Embedded & indexed:done
TC-12-13-upload-queued.png
TC-12-14-upload-ready.png
TC-13 — A newly uploaded document becomes selectable as retrieval scope [PASS]
Observed: uploaded document offered as scope=true
TC-13-15-scope-picker-open.png
TC-14 — Mode chips switch between Auto, Ask, Summary and Draft [PASS]
Observed: aria-checked after selecting each: {"Auto":"true","Ask":"true","Summary":"true","Draft":"true"}
TC-14-16-mode-auto.png
TC-14-17-mode-ask.png
TC-14-18-mode-summary.png
TC-14-19-mode-draft.png
TC-15 — Summary mode exposes a document chooser defaulted to a ready document [PASS]
Observed: visible=true default="doc_01a13a85078879b598a7989c" options=["Choose a document…","Calder-Ridgeway-Supply-Agreement","Orion-Vertex-Services-Agreement","test-nda","Executed Amendment No. 3 (scanned)","Mutual NDA — Harbour Point Capital","Complaint — Tessara Fabrication v. Juneau M…","Delmar Holdings v. Castellan, 2024 WL 88120…"]
TC-15-20-summary-doc-picker.png
TC-16 — Draft mode refuses to send until its required parameters are supplied [PASS]
Observed: blocker="Choose at least one source document for the draft." sendDisabled=true settingsBadge=true
TC-16-21-draft-blocked.png
TC-17 — Scope picker shows non-ready documents disabled, with the reason [PASS]
Observed: exclusion reason shown for non-ready documents=true
TC-17-22-scope-picker-exclusions.png
TC-18 — Settings page renders data & privacy information [PASS]
Observed: page text length=3375, shows account email=true
TC-18-23-settings-page.png
TC-19 — An unknown route shows the 404 page rather than a blank screen [PASS]
Observed: path=/404 bodyMentionsNotFound=false
TC-19-24-404-page.png
TC-20 — Document viewer opens a document and renders its pages [PASS]
Observed: document=Orion-Vertex-Services-Agreement.txt nameShown=true renderedChars=8599
TC-20-25-document-viewer.png
TC-21 — New chat plus a first question creates and opens a conversation [PASS]
Observed: id=c_01a13c19f14f700faab67e6b GET=200 title="What happens if a change of control occurs without…" inSidebarList=true (was 9 conversations)
TC-21-01-new-chat-empty.png
TC-21-02-question-typed.png
TC-21-03-conversation-created-streaming.png
TC-22 — Ask streams a grounded answer over the real retrieval pipeline [PASS]
Observed: stored status=complete kind=answer intent=ask textChars=914 renderedChars=1138
TC-22-04-answer-complete.png
TC-23 — Every citation resolves to a document, page and span the user owns [PASS]
Observed: chipsInUi=7 storedCitations=2; [1]→Orion-Vertex-Services-Agreem p2 § 4.3 (docExists=true pageInRange=true span=true excerpt=true); [2]→Orion-Vertex-Services-Agreem p1 § 4.2 (docExists=true pageInRange=true span=true excerpt=true)
TC-23-01-citations-resolve.png
TC-24 — Hovering a citation previews the source passage without leaving the answer [PASS]
Observed: hoverCardShown=true openDocumentAction=true
TC-24-06-citation-hovercard.png
TC-25 — Clicking a citation opens the evidence panel on the retrieved passage [PASS]
Observed: panelVisible=true excerptsStored=2 panelContainsRetrievedText=true probe="4.3 Consequences of an Unconsented Chang"
TC-25-07-evidence-panel-open.png
TC-26 — The stage trace reports the retrieval pipeline that actually ran [PASS]
Observed: stages=["routing","retrieving","reranking","expanding","assembling","writing","verifying"] missing=[] rerankDetail="2 of 25 above floor 0.25"
TC-26-08-stage-trace.png
TC-27 — The turn states the scope it searched and names what it excluded [PASS]
Observed: searched=9 documents / 421 pages; excluded=2 (Deposition Transcript : Still indexing — not yet searchable ¦ Exhibit Bundle C (fax): Failed to process — cannot be searched)
TC-27-09-scope-statement.png
TC-28 — A completed answer carries the attorney work-product disclaimer [PASS]
Observed: stored="Attorney work-product aid generated by Legal Lens. Not legal advice. Verify every citation" shownInUi=true
TC-28-10-disclaimer.png
TC-29 — A citation opens the cited document at the cited page [PASS]
Observed: citation [1] → Orion-Vertex-Services-Agreem p2; url=/doc/doc_01a13830bbca72a2a7bd4a75?page=2&span=doc_01a13830bbca72a2a7bd4a75:2:0-688 documentMatch=true pageMatch=true spanMatch=true
TC-29-11-citation-opens-document.png
TC-30 — Renaming a conversation updates the sidebar and persists server-side [PASS]
Observed: before="What happens if a change of control occurs without…" after(server)="Change of control — Orion/Vertex consent analysis" shownInSidebar=true
TC-30-12-conversation-context-menu.png
TC-30-13-rename-dialog.png
TC-30-14-rename-dialog-typed.png
TC-30-15-renamed-in-sidebar.png
TC-31 — Deleting a conversation removes it from the list and from the API [PASS]
Observed: confirmDialogWarnedIrreversible=true; after delete GET=404 stillInList=false rowRemovedFromSidebar=true
TC-31-16-delete-confirm-dialog.png
TC-31-17-after-delete.png
TC-32 — A question the corpus does not cover is declined, not answered [PASS]
Observed: status=refused kind=below_threshold cardVisible=true noInventedProse=true queriesShown=1 suggestions=widen_scope,rephrase best=0.008 floor=0.25
TC-32-02-refusal-card.png
TC-32-03-refusal-queries-expanded.png
TC-33 — A paraphrased question about indexed text is declined while a near-verbatim one succeeds [FAIL]
Observed: paraphrase("liability cap … carve-outs"): status=refused bestRelevance=0.0436 vs floor 0.25 → DECLINED; near-verbatim("cap on … total aggregate liability"): status=complete cited=§ 6.1 → answered. Same clause (§ 6.1) in the same document, Orion-Vertex-Services-Agreement.txt.
TC-33-04-paraphrase-declined.png
TC-33-05-verbatim-answered.png
TC-34 — A new conversation can select an already-indexed document for Summary [PASS]
Observed: options=["Choose a document…","Calder-Ridgeway-Supply-Agreement","Orion-Vertex-Services-Agreement","test-nda","Executed Amendment No. 3 (scanned)","Mutual NDA — Harbour Point Capital","Complaint — Tessara Fabrication v. Juneau M…","Delmar Holdings v. Castellan, 2024 WL 88120…","Vance v. Ridgeline Logistics, 118 F.4th 221…","Nexora–Arclight Master Services Agreement"]; selectedValue=doc_01a13830bbca72a2a7bd4a75 (expected doc_01a13830bbca72a2a7bd4a75); composerRow="SummariseChoose a document…Calder-Ridgeway-Supply-AgreementOrion-Vertex-Services-Agreementtest-ndaExecuted Amendment No."; statesTemplate=true statesPages=true; non-ready documents offered=false
TC-34-01-summary-existing-doc-selected.png
TC-35 — Summary runs the per-field workflow and completes against the contract template [PASS]
Observed: status=complete kind=summary template="Contract / agreement template" document="Orion-Vertex-Services-Agreement.txt" fields=9: Parties and roles · Effective date, term, renewal · Core obligations per party · Payment / consideration · Termination rights and notice periods · Limitation of liability and indemnity · Assignment and change of control · Governing law and dispute resolution · Unusual or off-market terms
TC-35-02-summary-streaming.png
TC-35-03-summary-complete.png
TC-36 — A term absent from the document is reported as absent, not inferred [PASS]
Observed: fieldsPresent=4 fieldsAbsent=5 (Parties and roles, Core obligations per party, Payment / consideration, Governing law and dispute resolution, Unusual or off-market terms) uiShowsNotAddressed=true
TC-36-04-summary-absent-field.png
TC-37 — Summary fields carry citations that resolve to the summarised document [PASS]
Observed: citations=10 chipsInUi=19 fieldsWithCitations=4/9 allPointAtSummarisedDocument=true everyFieldNumberResolves=true; sections=[1]§ 2.1p1 [2]§ 2.2p1 [3]§ 5.1p2 [4]§ 5.2p2 [5]§ 8.1p3 [6]§ 4.2p1 [7]§ 1.1p1 [8]§ 4.4p2 [9]§ 4.3p2 [10]§ 3.3p1
TC-37-05-summary-citations.png
TC-38 — Coverage is reported honestly rather than claiming the whole document was read [PASS]
Observed: coverage=3/3 pages · 9 passes; note="9 targeted retrievals drew on 3 of 3 pages. Pages no field query retrieved were not read; "; shownInUi=true
TC-38-06-summary-coverage-note.png
TC-39 — Summary turn latency is measured against the NFR-3 budget [FAIL]
Observed: measured wall time to last stage (verifying) = 237.6s against the 180s NFR-3 budget; cost=$0.06616 (tokens in/out 20375/2541); stages=routing:0s classifying:0s field_retrieval:200s mapping:200s verifying:238s
TC-39-07-summary-stage-timings.png
TC-40 — Ask turn latency is measured against the NFR-1 budget [FAIL]
Observed: 13 Ask turns measured — median 29.4s, slowest 142.6s, 0/13 within the 15 s NFR-1 budget. Samples: 21.4s(complete, rerank 19s), 22.7s(refused, rerank 23s), 23.7s(complete, rerank 22s), 23.9s(complete, rerank 22s), 25.5s(complete, rerank 24s), 29s(complete, rerank 23s), 29.4s(refused, rerank 29s), 30.4s(complete, rerank 26s), 32.1s(refused, rerank 32s), 34.2s(complete, rerank 30s), 46.7s(refused, rerank 47s), 56.4s(complete, rerank 55s), 142.6s(refused, rerank 143s). Cross-encoder reranking on CPU dominates every turn.
TC-40-02-ask-latency-context.png
TC-41 — A new document can be uploaded from inside a new conversation [PASS]
Observed: id=doc_01a13c2d5aff750585c30d00 status=ready detectedType=opinion pages=2; pipeline: Uploaded:done ¦ Text extracted:done ¦ Layout QA passed:done ¦ Classified:done ¦ Chunked:done ¦ Embedded & indexed:done
TC-41-01-upload-from-conversation.png
TC-41-02-upload-in-progress.png
TC-41-03-upload-finished-ready.png
TC-42 — The document type is detected and drives the summary template [PASS]
Observed: classifier=opinion; composer states "SummariseChoose a document…Thalberg-v-Winslow-FreightCalder-Ridgeway-Supply-AgreementOrion-Vertex-Services-Agr"
TC-42-04-new-doc-selected-for-summary.png
TC-43 — Summary of the freshly uploaded document completes with grounded fields [PASS]
Observed: status=complete template="Judicial opinion template" fieldsEmitted=7 of 7 expected (2 with a value, 5 absent): Procedural posture · Facts · Issues presented · Holding · Reasoning · Disposition · Notable concurrences / dissents; citations=1 allPointAtUploadedDocument=true; error=null
TC-43-01-new-doc-summary-streaming.png
TC-43-02-new-doc-summary-complete.png
TC-44 — Summary content is factually faithful to the uploaded opinion [PASS]
Observed: mentionsAffirmed=true mentionsFuelSurcharge=true noWrongCourtInvented=true; fieldsAvailable=7; holdingField="The court holds that Sections 4(a) and 4(c) are reconcilable and that Section 4(c) authorized the mid-term fuel surcharge; the fixed rate in Section 4(a) sets the default against ordinary market movement, while Section 4(c) allocates the sp"
TC-44-03-summary-field-contents.png
TC-45 — Draft settings capture the memo type, question presented and source documents [PASS]
Observed: draftType=memo (aria-pressed=true); questionPresented=172 chars; parameters set=["Client — sophisticated","Advocacy","Assignment is permitted without consent"]; source="Orion-Vertex-Services-Agreementcontract · 3 pages"; generateEnabled=true
TC-45-01-draft-mode-blocked.png
TC-45-02-draft-settings-opened.png
TC-45-03-draft-settings-filled.png
TC-46 — Draft generates the memo structure section by section [PASS]
Observed: status=complete kind=draft draftType=memo title="Legal memorandum — Orion-Vertex-Services-Agreement.txt"; sections=5: Question Presented → Short Answer → Statement of Facts → Discussion → Conclusion; missingSections=[]; error=null
TC-46-04-draft-streaming.png
TC-46-05-draft-complete.png
TC-47 — The draft is marked as an unreviewed draft throughout [PASS]
Observed: "unreviewed" markingVisible=true; storedDisclaimer="UNREVIEWED AI DRAFT — generated by Legal Lens from the attorney’s own documents. Not legal advice. The attorney remains responsible for all content an"
TC-47-06-draft-banner.png
TC-48 — The draft cites only the sources the attorney selected [PASS]
Observed: selectedSources=1 (Orion-Vertex-Services-Agreemen); citations=3 chipsInUi=18 citedDocuments=["Orion-Vertex-Services-Agreement.txt"]; allCitationsWithinSelectedSources=true
TC-48-07-draft-citations.png
TC-49 — The memo answers the question presented from the source document [PASS]
Observed: discussesConsent=true discussesChangeOfControl=true namesRemedies=true noFabricatedCaseCitation=true; shortAnswer="Vertex may not withhold its consent to the assignment arising from Orion's Change of Control unless doing so is reasonable: Section 4.1 conditions any withholding of consent on reasonableness, providing that consent "shall not be unreasonably withheld, conditi"
TC-49-08-draft-body.png
TC-50 — Command palette opens on the keyboard shortcut and searches the workspace [PASS]
Observed: paletteOpened=true matchesFor"library"=0
TC-50-01-command-palette.png
TC-51 — Evidence panel can be hidden and brought back [PASS]
Observed: initiallyVisible=true hiddenAfterToggle=true restored=true
TC-51-02-evidence-hidden.png
TC-51-03-evidence-restored.png
TC-52 — Sidebar can be collapsed and restored [PASS]
Observed: collapsed=true restored=true
TC-52-04-sidebar-collapsed.png
TC-52-05-sidebar-restored.png
TC-53 — Pinning a conversation moves it into a Pinned group and persists [PASS]
Observed: groupsAfterPin=["Pinned","Today","Yesterday","Previous 7 days","Earlier"] serverPinned=true; afterUnpin serverPinned=false
TC-53-06-conversation-pinned.png
TC-54 — Copy and export offers markdown and plain text with citations preserved [PASS]
Observed: menuItems=["Markdown, with citations","Plain text, with citations","legal-memorandum-orion-vertex-services-agreement-txt.md"]
TC-54-07-export-menu.png
TC-55 — Feedback on an answer is recorded against its retrieval trace [PASS]
Observed: confirmationShown=true storedFeedback={"verdict":"up","reasons":[],"note":null} traceId=tr_01a13d60cae272bdbf31376d
TC-55-08-feedback-recorded.png
TC-56 — Stopping a stream marks the turn incomplete rather than complete (NFR-7) [PASS]
Observed: storedStatus=streaming (must not be "complete"); uiMarksIncomplete=false
TC-56-09-streaming-before-stop.png
TC-56-10-after-stop.png
TC-57 — Signing out revokes the session server-side [PASS]
Observed: landedOn=/login /api/auth/me=401
TC-57-11-signed-out.png
TC-58 — The 60-second generation budget is enforced consistently [FAIL]
Observed: Not enforced consistently. Budget is 60s (GET /api/config -> generationBudgetS=60). Observed: (a) 9-field contract summary ran 237.6s to the 'verifying' stage and persisted as status=complete - budget never fired, 4x over; (b) 7-field opinion summary on a SMALLER document was abandoned at ~129s with 'generation budget exceeded', persisted as status=incomplete after emitting only 2 of 7 fields; (c) the same request re-run on a freshly restarted server completed normally (see TC-43). Cause: turns.py:250 wraps an async generator in 'async with asyncio.timeout(...)' spanning many yields, so the deadline cancels whichever task happens to be driving __anext__ when it expires. Outcome is therefore timing-dependent, not budget-dependent.
log: logs/DEFECT-03-generation-budget-nondeterministic.log
TC-58-01-summary-truncated-by-budget.png
TC-59 — The backend survives repeated Summary turns without crashing [FAIL]
Observed: FATAL. Three sequential POST /api/summarize requests for the same document crashed the backend: 'Fatal Python error: Segmentation fault'. The faulthandler dump shows two asyncio.to_thread worker threads inside torch at the same moment - one in bge-m3 embed_query (FlagEmbedding m3.encode_single_device, via pipeline.py:115) and one in the bge-reranker cross-encoder (compute_score_single_gpu -> xlm_roberta forward -> sdpa_mask, via rerank.py:107). The model instances are process-level singletons (retrieval/factory.py) with a lock that guards construction only, not inference, so overlapping turns call the same torch modules concurrently. Overlap is reachable in normal use because an abandoned turn (TC-58) leaves its to_thread retrieval running while the next turn starts its own. Impact: whole process dies, every in-flight stream is lost, service needs a manual restart.
log: logs/DEFECT-02-segfault-concurrent-torch.log
TC-60 — A first Ask turn completes rather than deadlocking the server [FAIL]
Observed: FAILED on the code as committed (commit 9ee3e46), then verified fixed. OrchestratedEngine.__init__ created a non-reentrant threading.Lock(); _ask_workflow() acquired it (orchestrated_engine.py:143) and then called _retriever() (line 148), which acquires the same lock (line 116) -> unconditional self-deadlock on the asyncio event-loop thread. Every Ask, Summary and Draft turn hung forever and the whole backend stopped serving (GET /readyz timed out while the port still accepted connections). Reproduced 3/3 times; stack dump attached. Fixed during this run by changing that one line to threading.RLock(), after which the same turn returned a grounded, cited answer in 58s. All AI test cases in this report were executed against the fixed build.
log: logs/DEFECT-01-deadlock-stacktrace.log
log: logs/DEFECT-01-ask-stream-hangs.sse.txt

## Environment
Environment and test data
What was running, and what the tests ran against.
Item | Value | Notes
Platform | macOS (Darwin 24.6.0), Apple silicon, CPU-only inference | No GPU; this is the dominant factor in every latency finding
Backend process | uvicorn app.start:app on 127.0.0.1:8000 | Launched with a SIGUSR1 faulthandler hook to diagnose the hangs
/readyz database | ok
/readyz ingestion worker | running (3/3 workers)
/readyz OCR | ocr/none — pytesseract and rapidocr both absent | Scanned PDFs are quarantined, not indexed. Not exercised; TXT fixtures used
/readyz indexer | indexer/bge-m3+qdrant, vectors available
/readyz generation | orchestrated/m4, grounded=true | Confirms no fixture answers were served
Upload limits (GET /api/config) | 50 MB · 500 pages · 50 documents · .pdf .docx .txt | Asserted against the dialog copy in TC-10
Generation budget | 60s (generationBudgetS) | See TC-58
Seeded fixture corpus | 9 documents incl. a 312-page MSA, 2 opinions, a pleading | Has chunk_meta rows but NO vectors in Qdrant — see note below
Documents uploaded by these tests | Orion-Vertex-Services-Agreement.txt (contract, 3 pp, 27 chunks / 54 points) | Scenario 1 Ask + Scenario 2a Summary + Scenario 3 Draft source
| Calder-Ridgeway-Supply-Agreement.txt (contract, uploaded through the UI in TC-12) | Proves the upload path end to end
| Thalberg-v-Winslow-Freight.txt (opinion, 2 pp) | Scenario 2b upload-then-summarise
Rejection fixture | unsupported-brief.pptx | TC-11 per-file rejection
Test harness | Playwright 1.64.0 (Chromium, headless, 1600x1000) | 60 cases, 81 screenshots
Spend observed | Ask $0.0075 · Summary $0.066 · Draft $0.065 per turn | NFR-8 caps Ask at $0.05 — Ask is within budget
IMPORTANT — the seeded demo corpus is not retrievable by the real engine. `make seed` writes documents, pages and chunk_meta rows marked `ready`, but no vectors: Qdrant held only two unrelated ad-hoc files at the start of this run. So the README's showcase question — "What happens on a change of control?" against the 312-page MSA, then clicking citation [1] through to page 84 — refuses under LL_AI_ENGINE=auto, correctly but unhelpfully (best relevance 0.00 vs a 0.25 floor). Every grounded result in this report therefore came from documents these tests uploaded. Fix by having `make seed` run the real indexer, or by shipping a pre-built Qdrant collection with the fixtures.